## Non-Voyager Tasks Tracket
Feature | User Story | Story ID | PR | Assignee | Status | Priority | Start Date | Anticipated Due Date | Completion | RBAC | Document Completion | Notes | M | T | W | T 2 | F | M 2 | T 3 | W 2 | T 4 | F 2 | M 3 | T 5 | W 3 | T 6 | F 3 | M 4 | T 7 | W 4 | T 8 | F 4 | M 5 | T 9 | W 5 | T 10
| #MDM Acknowledgment Form [SI-2679] |  | 289 | Sriram | 100% |  | 2026-02-25 | 2026-02-26 | TRUE | FALSE | FALSE
| #Collibra Workflows [SI-1411; SI-2014; SI-2267] |  | 210 | Sriram | 100% |  | 2026-02-26 | 2026-04-03 | TRUE | FALSE | FALSE | 3/6: JP will get status on this today 3/18: This work is done, just waiting for the code for deployment. SHould be closed by next week. 3/25: Raised a PR to DEV for review, once completed will raise a PR to DEV1
| Rehire-Reimagined Implementation Reconciliation - Analysis |  |  | Tom | OnHold |  | 2026-02-23 | 2/25/0206 | FALSE | FALSE | FALSE | 3/6: Dependency on Deloitte walkthrough scheduled through multiple sessions next week of March 9.
Code Review | [6 empty] | 2026-02-23 | 2026-02-27 | TRUE | FALSE | FALSE
| Joiner (prehire + NewHire)( Employee + NEP) |  |  | Rajesh | 100% |  | 2026-02-27 | 2026-02-27 | TRUE | FALSE | FALSE
| Leaver Day1,3 and 61 ( Employee + NEP) |  |  | Zack | 100% |  | 2026-02-23 | 2026-02-24 | TRUE | FALSE | FALSE
| Mover ( Employee + NEP) |  |  | Rajesh | 100% |  | 2026-02-27 | 2026-02-27 | TRUE | FALSE | FALSE
| LOA + ROA ( EMployee) |  |  | Zack | 100% |  | 2026-02-23 | 2026-02-24 | TRUE | FALSE | FALSE
| Suspension + Recall Suspension |  |  | Rajan | 100% |  | 2026-02-23 | 2026-02-27 | TRUE | FALSE | FALSE
| Conversion Emp - NEP & NEP - EMp |  |  | Rajan | 100% |  | 2026-02-23 | 2026-02-27 | TRUE | FALSE | FALSE
| Rehire |  |  | Rajan | 100% |  | 2026-02-23 | 2026-02-27 | TRUE | TRUE | FALSE
Attribute Mappings | [6 empty] | 2026-03-02 | 2026-03-09 | FALSE | FALSE | FALSE
| Attribute Crosswalk by Deloitte |  |  | All | 100% |  | 2026-03-02 | 2026-03-02 | TRUE | FALSE | FALSE
| Crosswalk with PS-HCM |  |  | All | 100% |  | 2026-03-03 | 2026-03-04 | TRUE | FALSE | FALSE
| Identity Attributes Target Mapping by Deloitte |  |  | All | 100% |  | 2026-03-02 | 2026-03-02 | TRUE | FALSE | FALSE
| Identity Attributes Target Mapping by IAM |  |  | All | 100% |  | 2026-03-03 | 2026-03-09 | FALSE | FALSE | FALSE | 3/6: Working session scheduled for today, likely to spill into next week 3/18: This work is done, just waiting for the code for deployment. SHould be closed by next week.
Tier1 Application Policy Changes | (Update Custom Object for LCM event Accounts) | [5 empty] | 2026-03-03 | 2026-04-03 | FALSE | FALSE | FALSE
| Azure Active Directory | SI-3026 |  | Rajesh | 100% |  | 2026-03-03 | 2026-04-03 | TRUE | FALSE | FALSE
| Duo | SI-3027 |  | Rajesh | 100% |  | 2026-03-03 | 2026-04-03 | TRUE | FALSE | FALSE
| G Suite |  |  | Zack | 100% |  | 2026-03-03 | 2026-04-03 | TRUE | FALSE | FALSE
| ServiceNow |  |  | Rajan | 80% |  | 2026-03-03 | 2026-04-03 | FALSE | FALSE | FALSE | New CR request for following attributes PER_PERSON_NAMES_F/KNOWN_AS (Preferred Name - Preffered First Name (old)) PER_PERSON_NAMES_F/SUFFIX (suffix) PER_PERSON_NAMES_F/PRE_NAME_ADJUNCT (prefix)
| ServiceNow - add OU in the provisioning policy to ServiceNow REQ0360788 | SI-3032 |  | Rajan |  |  |  |  | FALSE | FALSE | FALSE
| Invision |  |  | Jon | 90% |  | 2026-03-04 | 2026-04-03 | FALSE | FALSE | FALSE | Auth and aggregation work. Needs Github entry.
| Salesforce (Call Center) |  |  | Rajesh |  |  | 2026-03-04 | 2026-03-13 | FALSE | FALSE | FALSE | Not applicable - non functional , will not be pushed into Voyager, until this functionally working and a business case.
| ININD - Sovera for HIM |  | 190 | Rajan | 100% |  | 2026-03-04 | 2026-03-13 | TRUE | FALSE | FALSE
| Surgery Scheduling Manager |  |  | Jon | NA |  | 2026-03-04 | 2026-03-13 | FALSE | FALSE | FALSE | Not applicable - non functional
| Tableau-AllSites (Tableau-AscensionNational -?) |  |  | Siva | 80% |  | 2026-03-04 | 2026-04-03 | FALSE | FALSE | FALSE | Aggregations & Disable
Disconnected Applications | [6 empty] | 2026-03-02 | 2026-03-04 | FALSE | FALSE | FALSE
| IIQ for ServiceNow Service Desk |  | 259 | Sriram | 100% |  | 2026-03-02 | 2026-03-04 | TRUE | FALSE | FALSE | Dependency on roles, entitlements of disconnected apps for assignment group. Also, check whether the assignment groups are present in SNOW for testing.
| Disconnected Provisioning Code | SI-2782 |  | Rajesh / Rachid | 50% |  | 2026-02-26 | 2026-03-02 | FALSE | FALSE | FALSE | Open a RAID item with ServiceNOw for IAM team access. SI-2943 Dependency to load the metaData.
| Provisioning policies , provisioning & Deprovisioning - JDBC (Disconnected apps) | SI-2940 |  | Sriram | 50% |  | 2026-04-10 | 2026-04-17 | FALSE | FALSE | FALSE | Setup entitlement Meta data.
Extended Attributes | [6 empty] | 2026-03-02 | 2026-03-02 | FALSE | FALSE | FALSE
| Identity Attributes (Move only Valid Attributes) | SI-2872 | 291 | Rajan | 95% |  | 2026-03-03 | 2026-04-24 | FALSE | FALSE | FALSE
| Application Attributes ( Move only Valid Attributes) | SI-2942 | 189 | Rajan | 100% |  | 2026-03-05 | 2026-03-10 | TRUE | FALSE | FALSE | Review in progress with core team
| Entitlement Metadata Attributes ( Move only Valid Attributes) | SI-2943 | 290 | Ashish | 55% |  | 2026-04-10 | 2026-04-24 | FALSE | FALSE | FALSE
| Bundle Metadata Attributes ( Move only Valid Attributes) | SI-2944 |  | Rachid | 40% |  | 2026-04-12 | 2026-04-21 | FALSE | FALSE | FALSE
| Link Account Attributes and Metadata Sync | SI-2945 |  | Ashish | 15% |  | 2026-04-10 | 2026-04-24 | FALSE | FALSE | FALSE
PS - HCM Data changes | Reference Data Lookup Management - like Dept., Business Unit etc. |  |  | All | 20% |  | 2026-03-03 | 2026-04-10 | FALSE | FALSE | FALSE
| Department/BU/Jobcode Crosswalk |  |  | Rajan | 50% |  | 2026-04-06 | 2026-04-10 | FALSE | FALSE | FALSE
| Role Migration w.r.t new Dept/Jobcode/BUs/location code | SI-2843 |  | Surendra |  |  | 2026-04-11 | 2026-04-15 | FALSE | FALSE | FALSE
| Lifecycle Events and Workflow | SI-2885 |  | Rajan |  |  | 2026-04-06 | 2026-04-17 | FALSE | FALSE | FALSE
| Joiner |  |  | Rajan | 90% |  | 2026-04-06 | 2026-04-17 | FALSE | FALSE | FALSE
| Leaver |  |  | Rajan | 70% |  | 2026-04-06 | 2026-04-17 | FALSE | FALSE | FALSE
| conversion |  |  | Rajesh | 40% |  | 2026-04-06 | 2026-04-17 | FALSE | FALSE | FALSE
| emp class change |  |  | Rajan | 50% |  | 2026-04-06 | 2026-04-17 | FALSE | FALSE | FALSE
| Rehire |  |  | Rajan | 60% |  | 2026-04-06 | 2026-04-17 | FALSE | FALSE | FALSE
| Access Request Workflow |  |  | Rajan |  |  |  |  | FALSE | FALSE | FALSE
Miscellaneous | [6 empty] | 2026-03-02 | 2026-03-05 | FALSE | FALSE | FALSE
| Existing Custom Report | SI-2849 |  | Sriram | 20% |  | 2026-03-25 | 2026-04-10 | FALSE | FALSE | FALSE
| SOD Policies | SI-2901 | 257 | Sriram | 100% |  | 2026-03-04 | 2026-03-06 | TRUE | FALSE | FALSE
| IdentityIQ Settings Sync | SI-2894 |  | Jon | 90 |  | 2026-03-13 | 2026-03-27 | FALSE | FALSE | FALSE | Voyager PR218
| Task Definitions - multiple | SI-2946 |  | Rajan | 95% |  | 2026-03-11 | 2026-04-03 | FALSE | FALSE | FALSE
| Existing Certification | SI-2850 |  | Rajan (with Ed K) | 85% |  | 2026-02-26 | 2026-03-31 | FALSE | FALSE | FALSE | Cert requirement documents.
| #GWS Nested Groups Certification [SI-1876] | SI-2915 |  | Rajan |  |  | 2026-03-04 | 2026-04-10 | FALSE | FALSE | FALSE
| Task Schedules | SI-2948 |  | Rajan | 90% |  | 2026-03-19 | 2026-03-31 | FALSE | FALSE | FALSE | 81+ TaskSchedule objects
| Roles Analysis | SI-2842 |  | Zack | 100% |  | 2026-02-24 | 2026-02-27 | TRUE | FALSE | FALSE
| RBAC Engine and Application Access Request Quicklinks | SI-2884 |  | Surendra | 90% |  | 2026-03-04 | 2026-04-10 | FALSE | FALSE | FALSE
| Supervisor Self-Service form to reassign certification workitems | SI-2899 | 223 | Sriram | 100% |  | 2026-03-31 | 2026-04-06 | TRUE | FALSE | FALSE | 03/31: Raised a PR to DEV for review
| Quicklinks - | SI-2900 |  | Rachid | 90% |  | 2026-04-06 | 2026-04-15 | FALSE | FALSE | FALSE
| #Manage Mailbox License Quicklink | SI-2902 | 245 | Sriram | 100% |  | 2026-04-01 | 2026-04-10 | FALSE | FALSE | FALSE | 04/06: Raised a PR to DEV, need to still complete the Rule library reference w.r.t voyager attributes and logic
| Regression Test cases - development |  |  | Siva |  |  | 2026-03-02 | 2026-04-10 | FALSE | FALSE | FALSE
| Terminate the Active sessions on EntraID ? | SI-2881 |  | Rajesh |  |  | 2026-04-06 | 2026-04-10 | FALSE | FALSE | FALSE
| Identity Warehouse configuration | SI-2882 |  | Jon/Rachid | 90% |  | 2026-03-27 | 2026-04-02 | FALSE | FALSE | FALSE | Voyager PR219
| Advanced Analytics configurations | SI-2889 |  | Jon/Rachid | 40% |  | 2026-04-06 | 2026-04-10 | FALSE | FALSE | FALSE
| Ops console Migration | SI-2848 | 249 | Sriram | 100% |  | 2026-04-06 | 2026-04-17 | FALSE | FALSE | FALSE | 04/08: Raised a PR to DEV
| IdentityIQ SSO Configuration | SI-2877 |  | Rajesh | 75% |  | 2026-04-02 | 2026-04-06 | FALSE | FALSE | FALSE
| Bundle and Entitlement Update Workflows | SI-2886 | 250 | sriram | 100% |  | 2026-04-08 | 2026-04-17 | TRUE | FALSE | FALSE | 04/08: There is no bundle update workflow configured. Raised a PR for Entitlement update workflow to DEV
| Access Catalog Setup and Configurations | SI-2887 |  | Surendra | 90% |  | 2026-04-10 | 2026-04-15 | FALSE | FALSE | FALSE
| Access Catalog - Role - Sunrise and Sunset features | SI-2891 |  | Surendra | 90% |  | 2026-04-10 | 2026-04-15 | FALSE | FALSE | FALSE
| Audit Events reconciliation | SI-2888 |  | Rajan | 20% |  | 2026-03-18 | 2026-04-10 | FALSE | FALSE | FALSE
| Notification and Email Templates | SI-2893 |  | Rajan | 20% |  | 2026-03-20 | 2026-04-17 | FALSE | FALSE | FALSE
| #Reconcile Duo AD Groups [SI-2020] | SI-2890 |  | Jon | 90% |  | 2026-04-01 | 2026-04-10 | FALSE | FALSE | FALSE | Voyager PR220
| Source Code (Unified Code Framework and jar files) | SI-2892 |  | Rajesh |  |  | 2026-04-06 | 2026-04-14 | FALSE | FALSE | FALSE
| Failed workflow workitems management | SI-2895 |  | JP |  |  | 2026-04-06 | 2026-04-10 | FALSE | FALSE | FALSE
| Delegation Management | SI-2846 |  | Surendra | 30% |  | 2026-03-30 | 2026-04-10 | FALSE | FALSE | FALSE | Leaver in Scope
| AAM training site contenet Review | [7 empty] | FALSE | FALSE | FALSE
| AD Domain Normalization |  |  | Surendra |  |  |  |  | FALSE | FALSE | FALSE
| SOP Document transistions | SI-2977 |  | Zack / Rajan |  |  | 2026-04-01 | 2026-04-14 | FALSE | FALSE | FALSE
| Gsuite redesign for Voyager |  |  | Rajesh / Rachid |  |  |  |  | FALSE | FALSE | FALSE
| Code Review |  |  | Rajesh / Rajan / JP |  |  | 2026-04-10 |  | FALSE | FALSE | FALSE
| AD Domain Redundancy forAggregation and Provisioning | SI-2988 | 1058 | Rachid |  |  |  |  | FALSE | FALSE | FALSE

## Testing Non-Voyager Tasks Track
Feature | User Story | Story ID | Test Cases | Deployment Ready | Testing Completion | Assignee | Status | Priority | Start Date | Anticipated Due Date | Test cases Links & Notes | M | T | W | T 2 | F | M 2 | T 3 | W 2 | T 4 | F 2 | M 3 | T 5 | W 3 | T 6 | F 3 | M 4 | T 7 | W 4 | T 8 | F 4 | M 5 | T 9 | W 5 | T 10
Deloitte Test cases |  |  |  | FALSE | FALSE
Joiner (prehire + NewHire)( Employee + NEP)
Leaver Day1,3 and 61 ( Employee + NEP)
Mover ( Employee + NEP)
LOA + ROA ( EMployee)
Suspension + Recall Suspension
Conversion Emp - NEP & NEP - EMp
Rehire
Attribute Mappings
| Attribute Crosswalk by Deloitte |  |  |  |  | All
| Crosswalk with PS-HCM |  |  |  |  | All
| Identity Attributes Target Mapping |  | Pending |  |  | All |  |  |  |  | Note: Disable attribute sync in the Refresh task definitions.
Tier1 Application Policy Changes | (Update Custom Object for LCM event Accounts)
| Azure Active Directory |  | Pending |  |  | Rajesh
| Duo |  | Pending |  |  | Rajesh
| G Suite |  |  |  |  | Zack
| ServiceNow |  | Pending |  |  | Rajan |  |  |  |  | Pull in all Test cases w.r.t replatforming and share with Siva. update LCM test cases with additional step to verify the ServiceNow account & entitlement(in applicable). https://docs.google.com.mcas.ms/spreadsheets/d/1Thxdh3CZqHWiJ40UhLgYuVcFjtSanfz7rfv96R6_BOo/edit?gid=0#gid=0 https://docs.google.com.mcas.ms/document/d/1mShoTq0490Vv9cuo0lWetTu-hLQoHPXSjB9B6eI3Oxo/edit?tab=t.0#heading=h.i9rk71u0kl9m
| Invision |  |  |  |  | Jon
| Salesforce (Call Center) |  |  |  |  | Rajesh
| ININD - Sovera for HIM |  | Pending |  |  | Rajan
| Surgery Scheduling Manager |  |  |  |  | Jon
| Tableau-AllSites (Tableau-AscensionNational -?) |  |  |  |  | Siva
Disconnected Applications
| IIQ for ServiceNow Service Desk |  | Pending |  |  | Sriram
| Disconnected Provisioning Code |  | Pending |  |  | Rajesh / Rachid
| Provisioning policies , provisioning & Deprovisioning - JDBC (Disconnected apps) | SI-2940 | Pending |  |  | Sriram
Extended Attributes
| Application Attributes ( Move only Valid Attributes) | SI-2942 |  |  |  | Rajan
| Entitlement Metadata Attributes ( Move only Valid Attributes) | SI-2943 | Pending |  |  | Ashish |  |  |  |  | Health Check test cases
| Bundle Metadata Attributes ( Move only Valid Attributes) | SI-2944 |  |  |  | Rachid
| Link Account Attributes and Metadata Sync | SI-2945 | Pending |  |  | Ashish |  |  |  |  | Health Check test cases
PS - HCM Data changes | Reference Data Lookup Management - like Dept., Business Unit etc. |  |  |  |  | All
| Department/BU/Jobcode Crosswalk |  |  |  |  | Rajan |  |  |  |  | Note: Disable attribute sync in the Refresh task definitions.
| Role Migration w.r.t new Dept/Jobcode/BUs/location code | SI-2843 |  |  |  | Surendra
| Lifecycle Events and Workflow | SI-2885 |  |  |  | Rajan |  |  |  |  | Health Check test cases & functional Test cases
| Joiner |  |  |  |  | Rajan
| Leaver |  |  |  |  | Rajan
| conversion |  |  |  |  | Rajesh
| emp class change |  |  |  |  | Rajan
| Rehire |  |  |  |  | Rajan
Miscellaneous | [10 empty] | Health Check test cases & functional Test cases
| #MDM Acknowledgment Form [SI-2679] |  | Pending |  |  | Sriram
| #Collibra Workflows [SI-1411; SI-2014; SI-2267] |  | Pending |  |  | Sriram |  |  |  |  | https://docs.google.com.mcas.ms/document/d/1Q9UIcR7zNu1w7RoJf5kc8RKci6Bwp3Devi36wx1GAkg/edit?tab=t.0#heading=h.7ett5xka9ilb
| Rehire-Reimagined Implementation Reconciliation - Analysis |  |  |  |  | Tom
| Existing Custom Report | SI-2849 | Pending |  |  | Sriram
| SOD Policies | SI-2901 | Pending |  |  | Sriram |  |  |  |  | https://docs.google.com/spreadsheets/d/1WqaJSLxyvNnqbuRywKTavqOrXo9FOWDC-LyP-Zycses/edit?usp=sharing
| IdentityIQ Settings Sync | SI-2894 |  |  |  | Jon
| Task Definitions - multiple | SI-2946 | Pending |  |  | Rajan
| Existing Certification | SI-2850 | Pending |  |  | Rajan (with Ed K)
| #GWS Nested Groups Certification [SI-1876] | SI-2915 | Pending |  |  | Rajan
| Task Schedules | SI-2948 | Pending |  |  | Rajan |  |  |  |  | Health Check test case Only.
| Roles Analysis | SI-2842 |  |  |  | Zack
| RBAC Engine and Application Access Request Quicklinks | SI-2884 | Completed |  |  | Surendra |  |  |  |  | https://docs.google.com.mcas.ms/spreadsheets/d/1dEPoYeeKtNC7q7m9I8alCpL67jIb2uKQsmwNK_F8V5w/edit?gid=0#gid=0
| Supervisor Self-Service form to reassign certification workitems | SI-2899 | Pending |  |  | Sriram |  |  |  |  | https://docs.google.com.mcas.ms/spreadsheets/d/1vHtkDZyh2t0bUb3_qEZjpHsKDxqqhOpt8mRUzuUxBtY/edit?gid=0#gid=0
| Quicklinks - | SI-2900 | Pending |  |  | Rachid
| #Manage Mailbox License Quicklink | SI-2902 | Pending |  |  | Sriram
| Regression Test cases - development |  |  |  |  | Siva
| Terminate the Active sessions on EntraID ? | SI-2881 |  |  |  | Rajesh
| Identity Warehouse configuration | SI-2882 | Pending |  |  | Jon/Rachid
| Advanced Analytics configurations | SI-2889 | Pending |  |  | Jon/Rachid
| Ops console Migration | SI-2848 | Pending |  |  | Sriram
| IdentityIQ SSO Configuration | SI-2877 | Pending |  |  | Rajesh |  |  |  |  | Health Check test case Only.
| Bundle and Entitlement Update Workflows | SI-2886 | Pending |  |  | sriram
| Access Catalog Setup and Configurations | SI-2887 | Pending |  |  | Surendra |  |  |  |  | also include Health Check for UI verification Only.
| Access Catalog - Role - Sunrise and Sunset features | SI-2891 | Pending |  |  | Surendra
| Audit Events reconciliation | SI-2888 | Pending |  |  | Rajan
| Notification and Email Templates | SI-2893 |  |  |  | Rajan |  |  |  |  | As part of LCM, Link to LCM , Workitems , approvals & certs
| #Reconcile Duo AD Groups [SI-2020] | SI-2890 |  |  |  | Jon |  |  |  |  | Health Check test case Only.
| Source Code (Unified Code Framework and jar files) | SI-2892 | N/A |  |  | Rajesh |  |  |  |  | Overall deployment health covers it.
| Failed workflow workitems management | SI-2895 |  |  |  | JP
| Delegation Management | SI-2846 | Pending |  |  | Surendra
AAM training site contenet Review
| AD Domain Normalization |  |  |  |  | Vikas
| SOP Document transistions | SI-2977 |  |  |  | Zack / Rajan
| Gsuite redesign for Voyager |  |  |  |  | Rajesh / Rachid
| Code Review |  |  |  |  | Rajesh / Rajan / JP

## Schedule
Project Timeline Overview
Phase 1: Lifecycle Workflow Code Review and Analysis (Feb 23 – Feb 27)
Phase 2: Attribute Mapping & Tier 1 App Integration (Feb 25 – Feb 27)
Phase 3: Provisioning Policies & Metadata Sync (March 2 – March 5)
Phase 4: Role RBAC & System Configuration (March 4 – March 12)
Phase 5: Unit Testing and Code Consolidation(March 13 – March 27)
1. Identity Lifecycle Management (LCM)
Joiners/Movers/Leavers: Handling both employees and Non-Employee Partners (NEP).
Special Statuses: Managing Leave of Absence (LOA), Suspensions, and Rehires.
Rehire-Reimagined: A specific focus on reconciling rehire implementations
2. Tier 1 Application Provisioning Policy Changes
Cloud Apps: Azure AD (Entra ID), G Suite, Duo, and Invision.
Service Management: ServiceNow.
Business/Clinical Apps: Salesforce, Tableau, and Surgery Scheduling Manager.
3. Data Governance & Attribute Mapping
Attribute Crosswalks: Mapping identity attributes to target systems.
Metadata Sync: Moving valid attributes for Applications, Entitlements, and Bundles.
Reference Data: Managing lookups for Departments and Business Units.
4. RBAC & System Optimization
RBAC & Roles: Role analysis and migration based on new Job Codes and BUs.
Governance: SOD (Segregation of Duties) policies and GWS Nested Groups Certification.
Self-Service: Implementing Quicklinks for mailbox licenses and supervisor reassignment forms.
5. Unit Testing and consolidation of Regression Test cases.
Code consolidation and checkin
Resgression Test cases review and execution
Timeframe: | 2/23 - 3/30

## Weekly Time Log Report
2026-04-19 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
| Ashish | SI-2943; SI-2945 | 50% | SI-2627;SI-2836;SI3024 | 50%
| Jonathan | SI-2994, SI-2890, SI-2984, SI-3034 | 35% | SI-3020, SI-3019, SI-2861 | 65%
| Rajesh | SI-2974, SI-2782, SI-3027, SI-3015, Code Reviews,Entitlement Attributes, SSL and other Platform support | 40% | SI-3013, SI-3014 | 60%
Zack
| Rajan | SI-2950, SI-2885, SI-2929, SI-3025, SI-3030, SI-2850, GSuite Assignment Rule, AD Domain Normalization, Reviews of QuickLinks, Metadata attributes (Bundle, Application, Entitlement) and other stories. | 70% | Production Support AD-AID Decommission Rehire-Reimagined Hypercare, Bug Fixes and Support Attestations - AdminOU and CyberArk | 30%
| Rachid | SI-2900, SI-2944, SI-2988, SI-2889, SI-2882 | 40%
| Surendra | SI-2884,SI-2843,SI-2887, SI-2891, SI-2846 | 50% | SI-2838,SI-2978 | 50%
Sriram
| Kannan |  |  | SI-2954,SI-3002 | 100%
2026-04-26 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-05-03 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-05-10 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-05-17 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-05-24 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-05-31 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-06-07 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-06-14 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-06-21 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-06-28 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-07-05 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-07-12 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-07-19 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-07-26 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-08-02 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-08-09 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan
2026-08-16 | Developers | Voyager Stories | Pecentage of Utilization/week | Non- Voyager Prod support Work | Pecentage of Utilization/week
Ashish
Jonathan
Rajesh
Zack
Rajan
Rachid
Surendra
Sriram
Kannan

## Resource Allocation
Resource Name | email ID | Hours/Week
Joshua Zack Pendleton | joshua.pendleton@ascension.org | 30
Rajesh Saka | rajesh.saka@ascension.org | 30
Ashish Patel | ashish.patel@ascension.org | 20
Jonathan Zelkowski | jonathan.zelkowski@ascension.org | 20
Sriram Mummidi | sriram.mummidi@ascension-external.org | 30
Rajan Kumar | rajan.kumar@ascension-external.org | 30
Surendra Vitla | surendra.vitla@ascension-external.org | 30